## Slide 1
DATA MIGRATION & ENVIRONMENT CREATION STATUS
STEERCO REPORT | PAGE C1 | SLIDE 4
STREAM-LEVEL PROGRESS
DATA LOAD PROGRESS DASHBOARD
TIMELINE & TARGET DATES
13-JAN13-FEB13-MARMARAPRMAY
PROGRESS VISUALIZATION (VS PLAN)
NOTES & CONSIDERATIONS
ENVIRONMENT CREATION: STREAM STATUS
● 57.0% Done ● 24.8% In Progress ● 18.2% Not Started
CRITICAL DEPENDENCIES & BLOCKERS
CRITICAL PATH DEPENDENCY: Code awaited from external partner [SF].
Impact: Currently delaying 12 key integration environments.
Expected resolution: TBD (Under active management).
TOTAL LOADED
1570 UNITS
41% | Max Projected: 3836
CURRENT VELOCITY
70/DAY
Target: 100/day
ORIGINAL PLAN (3310)
MAX PROJECTED (3836)
Current velocity is 70/day; target to reach 100/day.
Bulk-operation admin role should help improve data load turnaround time.
SIT reupload requests and lab support increased effort significantly.
Bank Certification + Labs + Interops would require significant effort and reduce velocity.
STATUS OVERVIEW
(Target: 100% Completion)
CORE SIT/UAT
DATABASE LAYER
INTEGRATION & INTEROPS
PERIPHERAL TOOLS
•
•
•
•

## Slide 2
Image Sources
https://cdn.freebiesupply.com/logos/large/2x/societe-generale-2-logo-black-and-white.png
Source: freebiesupply.com