## Configuration
Parameter | Value | Description
Exec Time per Job (Mins) | 30 | Avg time to run CTRL-M job & monitor log
Valid Time per Table (Mins) | 45 | Avg time to run Snowpark comparator & verify
Number of Testers | 2 | Number of resources assigned
Productive Hours/Day | 6.5 | Hours available for testing (minus meetings)
Defect Buffer | 20% | Contingency for bugs/re-runs
Env Setup Lag (Days) | 5 | Days needed to finish the 5 pre-reqs

## Scope 2 Plan
Scope | Trigram | Start Date | Ctrl-M Jobs | Tgt Tables | Raw Effort (Hrs) | Total Effort w/ Buffer | Days Needed | Env Ready Date | Est. Completion Date | Risk Level | Jobs Completed | Tables Verified | Total Progress % | Assigned Tester | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05
2 | BVN | 2025-10-30 | 54 | 52 | 66 | 79.2 | 6.0923 | 2025-11-06 | 2025-11-14 | LOW | 1 | 2 | 2.83% | T1
2 | CLS | 2025-10-31 | 6 | 20 | 18 | 21.6 | 1.6615 | 2025-11-07 | 2025-11-10 | LOW | 1 | 2 | 11.54% | T7
2 | EXR | 2025-11-01 | 0 | 1 | 0.75 | 0.9 | 0.069231 | 2025-11-07 | 2025-11-07 | LOW | 0 | 1 | 100% | T8
2 | GUA | 2025-11-02 | 8 | 19 | 18.25 | 21.9 | 1.6846 | 2025-11-07 | 2025-11-10 | LOW | 1 | 2 | 11.11% | T6
2 | HTR | 2025-11-03 | 73 | 46 | 71 | 85.2 | 6.5538 | 2025-11-10 | 2025-11-18 | LOW | 1 | 2 | 2.521% | T2
2 | MPI | 2025-11-04 | 1 | 2 | 2 | 2.4 | 0.18462 | 2025-11-11 | 2025-11-11 | LOW | 1 | 2 | 100% | T7 (Queue)
2 | OBR | 2025-11-05 | 1 | 1 | 1.25 | 1.5 | 0.11538 | 2025-11-12 | 2025-11-12 | LOW | 1 | 2 | 150% | T6 (Queue)
2 | PYC | 2025-11-06 | 121 | 210 | 218 | 261.6 | 20.1231 | 2025-11-13 | 2025-12-11 | CRITICAL | 1 | 2 | 0.9063% | T1
2 | SHP | 2025-11-07 | 25 | 54 | 53 | 63.6 | 4.8923 | 2025-11-14 | 2025-11-20 | LOW | 1 | 2 | 3.797% | T3
2 | TRT | 2025-11-08 | 3 | 55 | 42.75 | 51.3 | 3.9462 | 2025-11-14 | 2025-11-19 | LOW | 1 | 2 | 5.172% | T8 (Queue)
2 | ULF | 2025-11-09 | 12 | 36 | 33 | 39.6 | 3.0462 | 2025-11-14 | 2025-11-19 | LOW | 1 | 2 | 6.25% | T5
2 | CNE | 2025-11-10 | 0 | 0 | 0 | 0 | 0 | 2025-11-17 | 2025-11-17 | LOW | 1 | 2 | 0% | TBD

## Readiness Tracker
Trigram | 1. Linux VM | 2. CTRL-M Config | 3. Data Copy | 4. Code Deploy | 5. Comparator | STATUS | Owner
BVN | No | No | No | No | No | BLOCKED
CLS | No | No | No | No | No | BLOCKED
EXR | No | No | No | No | No | BLOCKED
GUA | No | No | No | No | No | BLOCKED
HTR | No | No | No | No | No | BLOCKED
MPI | No | No | No | No | No | BLOCKED
OBR | No | No | No | No | No | BLOCKED
PYC | No | No | No | No | No | BLOCKED
SHP | No | No | No | No | No | BLOCKED
TRT | No | No | No | No | No | BLOCKED
ULF | No | No | No | No | No | BLOCKED
CNE | No | No | No | No | No | BLOCKED