## Dashboard
| Please Select a Project to View Related Tasks & Gantt: | [5 empty] | All Projects | 80 Tasks Found | [6 empty] | Gantt. Scroll | [6 empty] | 0
| Dashboard |  |  |  |  | Task ID | Top Tasks | Responsible | Start Date | End Date | Days Req. | Status | Days Comp. | Project | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20
[5 empty] | 0 | 0 | 0 | 1 | 2 | 4 | 3 | 4 |  | -1
[6 empty] | 1 | Project 1 - Task 1 | Person 1 | 2025-01-09 | 2025-01-28 | 20 | 100% | 20 | Project 1
|  | Overall Progress |  |  |  | 2 | Project 3 - Task 1 | Person 2 | 2025-01-10 | 2025-01-15 | 6 | 40% | 2.4 | Project 1
[6 empty] | 3 | Project 1 - Task 2 | Person 3 | 2025-01-11 | 2025-01-20 | 10 | 45% | 4.5 | Project 1
[6 empty] | 4 | Project 1 - Task 3 | Person 4 | 2025-01-14 | 2025-01-22 | 9 | 85% | 7.65 | Project 1
[6 empty] | 5 | Project 1 - Task 4 | Person 5 | 2025-01-10 | 2025-02-08 | 30 | 45% | 13.5 | Project 1
[6 empty] | 6 | Project 1 - Task 5 | Person 1 | 2025-01-13 | 2025-01-24 | 12 | 80% | 9.6 | Project 1
|  | Start Date |  | 2025-01-05 |  | 7 | Project 1 - Task 6 | Person 2 | 2025-01-13 | 2025-02-24 | 43 | 10% | 4.3 | Project 1
|  | End Date |  | 2025-03-08 |  | 8 | Project 1 - Task 7 | Person 3 | 2025-01-15 | 2025-02-06 | 23 | 50% | 11.5 | Project 1
|  | Overall Progress |  | 48.81% |  | 9 | Project 1 - Task 8 | Person 4 | 2025-01-15 | 2025-01-23 | 9 | 10% | 0.9 | Project 1
|  |  |  | 51.19% |  | 10 | Project 1 - Task 9 | Person 5 | 2025-01-16 | 2025-01-21 | 6 | 30% | 1.8 | Project 1
|  | Days Required |  | 62 days |  | 11 | Project 2 - Task 1 | Person 1 | 2025-01-06 | 2025-01-12 | 7 | 45% | 3.15 | Project 2
|  |  |  | 633 man-days |  | 12 | Project 2 - Task 2 | Person 2 | 2025-01-10 | 2025-01-18 | 9 | 100% | 9 | Project 2
[6 empty] | 13 | Project 2 - Task 3 | Person 3 | 2025-01-11 | 2025-01-18 | 8 | 50% | 4 | Project 2
[6 empty] | 14 | Project 2 - Task 4 | Person 4 | 2025-01-13 | 2025-01-19 | 7 | 60% | 4.2 | Project 2
|  | TOTAL TASKS | 80 | 80 |  | 15 | Project 2 - Task 5 | Person 5 | 2025-01-14 | 2025-01-17 | 4 | 70% | 2.8 | Project 2
|  | Not Started(0%) | 3 | 3 |  | 16 | Project 2 - Task 6 | Person 1 | 2025-01-14 | 2025-01-19 | 6 | 55% | 3.3 | Project 2
|  | Inprogress(1-99%) | 73 | 73 |  | 17 | Project 2 - Task 7 | Person 2 | 2025-01-17 | 2025-01-22 | 6 | 75% | 4.5 | Project 2
|  | 1-25% | 23 | 23 |  | 18 | Project 2 - Task 8 | Person 3 | 2025-01-18 | 2025-01-21 | 4 | 0% | 0 | Project 2
|  | 26-50% | 18 | 18 |  | 19 | Project 2 - Task 9 | Person 4 | 2025-01-20 | 2025-01-26 | 7 | 10% | 0.7 | Project 2
|  | 51-75% | 17 | 17 |  | 20 | Project 2 - Task 10 | Person 5 | 2025-01-09 | 2025-01-11 | 3 | 85% | 2.55 | Project 2
|  | 76-99% | 15 | 15 |  | 21 | Project 3 - Task 2 | Person 1 | 2025-01-05 | 2025-01-14 | 10 | 90% | 9 | Project 3
|  | Completed(100%) | 4 | 4 |  | 22 | Project 3 - Task 3 | Person 2 | 2025-01-14 | 2025-01-18 | 5 | 85% | 4.25 | Project 3
[6 empty] | 23 | Project 3 - Task 4 | Person 3 | 2025-01-16 | 2025-01-22 | 7 | 70% | 4.9 | Project 3
[6 empty] | 24 | Project 3 - Task 5 | Person 4 | 2025-01-19 | 2025-01-25 | 7 | 25% | 1.75 | Project 3
| Project Management Template By Excelx.com ¦ Powered by Analysistabs® |  |  | Developer by: PNRao |  | 25 | Project 3 - Task 6 | Person 5 | 2025-01-21 | 2025-01-23 | 3 | 100% | 3 | Project 3
Please let us know your feedback. 📧 Email: info@analysistabs.com |  | ℹ️ This is a free template that you can use to plan a small project with up to 25 tasks. 👉 Check out our premium templates for managing multiple projects and accessing more features.
49%
4Get the Full Version
4 Check 120+ Premium Project Management Templates

## Projects
Project Management
Projects | Tasks | Start | End | Days | %Progress | Remaining
All Projects | 80 | 2025-01-05 | 2025-03-08 | 633 | 48.81% | 51.19%
Project 1 | 10 | 2025-01-09 | 2025-02-28 | 168 | 49.5% | 50.5%
Project 2 | 10 | 2025-01-06 | 2025-01-29 | 61 | 55% | 45%
Project 3 | 5 | 2025-01-05 | 2025-01-31 | 32 | 74% | 26%
Project 4 | 7 | 2025-01-09 | 2025-02-03 | 51 | 23.57% | 76.43%
Project 5 | 8 | 2025-01-12 | 2025-02-02 | 55 | 67.5% | 32.5%
Project 6 | 8 | 2025-01-09 | 2025-01-25 | 52 | 50% | 50%
Project 7 | 9 | 2025-01-06 | 2025-01-26 | 62 | 41.11% | 58.89%
Project 8 | 11 | 2025-01-05 | 2025-02-03 | 69 | 41.82% | 58.18%
Project 9 | 4 | 2025-01-12 | 2025-01-28 | 28 | 57.5% | 42.5%
Project 10 | 8 | 2025-01-12 | 2025-02-02 | 55 | 40.62% | 59.38%
ℹ️ This is a free template that you can use to plan a small project with up to 25 tasks. 👉 Check out our premium templates for managing multiple projects and accessing more features.
Formulas:
Start = MIN(Table1[Start Date])
Start = MIN(IF(Table1[Project]=[Projects],Table1[Start Date]))
End = MAX(Table1[Start Date])+MAX(Table1[Days Required])
End = MAX(IF(Table1[Project]=[Projects],Table1[Start Date]))+MAX(IF(Table1[Project]=[Projects],Table1[Days Required]))
1.
Input Your Project Titles Here
4Get the Full Version
4 Check 120+ Premium Project Management Templates

## Tasks
Project | Task | Responsible | Start Date | Days Required | Progress
Project 1 | Project 1 - Task 1 | Person 1 | 2025-01-09 | 20 | 100%
Project 1 | Project 3 - Task 1 | Person 2 | 2025-01-10 | 6 | 40%
Project 1 | Project 1 - Task 2 | Person 3 | 2025-01-11 | 10 | 45%
Project 1 | Project 1 - Task 3 | Person 4 | 2025-01-14 | 9 | 85%
Project 1 | Project 1 - Task 4 | Person 5 | 2025-01-10 | 30 | 45%
Project 1 | Project 1 - Task 5 | Person 1 | 2025-01-13 | 12 | 80%
Project 1 | Project 1 - Task 6 | Person 2 | 2025-01-13 | 43 | 10%
Project 1 | Project 1 - Task 7 | Person 3 | 2025-01-15 | 23 | 50%
Project 1 | Project 1 - Task 8 | Person 4 | 2025-01-15 | 9 | 10%
Project 1 | Project 1 - Task 9 | Person 5 | 2025-01-16 | 6 | 30%
Project 2 | Project 2 - Task 1 | Person 1 | 2025-01-06 | 7 | 45%
Project 2 | Project 2 - Task 2 | Person 2 | 2025-01-10 | 9 | 100%
Project 2 | Project 2 - Task 3 | Person 3 | 2025-01-11 | 8 | 50%
Project 2 | Project 2 - Task 4 | Person 4 | 2025-01-13 | 7 | 60%
Project 2 | Project 2 - Task 5 | Person 5 | 2025-01-14 | 4 | 70%
Project 2 | Project 2 - Task 6 | Person 1 | 2025-01-14 | 6 | 55%
Project 2 | Project 2 - Task 7 | Person 2 | 2025-01-17 | 6 | 75%
Project 2 | Project 2 - Task 8 | Person 3 | 2025-01-18 | 4 | 0%
Project 2 | Project 2 - Task 9 | Person 4 | 2025-01-20 | 7 | 10%
Project 2 | Project 2 - Task 10 | Person 5 | 2025-01-09 | 3 | 85%
Project 3 | Project 3 - Task 2 | Person 1 | 2025-01-05 | 10 | 90%
Project 3 | Project 3 - Task 3 | Person 2 | 2025-01-14 | 5 | 85%
Project 3 | Project 3 - Task 4 | Person 3 | 2025-01-16 | 7 | 70%
Project 3 | Project 3 - Task 5 | Person 4 | 2025-01-19 | 7 | 25%
Project 3 | Project 3 - Task 6 | Person 5 | 2025-01-21 | 3 | 100%
Project 4 | Project 4 - Task 1 | Person 1 | 2025-01-23 | 9 | 10%
Project 4 | Project 4 - Task 2 | Person 2 | 2025-01-24 | 10 | 50%
Project 4 | Project 4 - Task 3 | Person 3 | 2025-01-09 | 4 | 25%
Project 4 | Project 4 - Task 4 | Person 4 | 2025-01-12 | 8 | 35%
Project 4 | Project 4 - Task 5 | Person 5 | 2025-01-15 | 10 | 30%
Project 4 | Project 4 - Task 6 | Person 1 | 2025-01-18 | 6 | 5%
Project 4 | Project 4 - Task 7 | Person 2 | 2025-01-18 | 4 | 10%
Project 5 | Project 5 - Task 1 | Person 3 | 2025-01-21 | 8 | 100%
Project 5 | Project 5 - Task 2 | Person 4 | 2025-01-23 | 9 | 90%
Project 5 | Project 5 - Task 3 | Person 5 | 2025-01-13 | 5 | 75%
Project 5 | Project 5 - Task 4 | Person 1 | 2025-01-12 | 3 | 80%
Project 5 | Project 5 - Task 5 | Person 2 | 2025-01-14 | 7 | 10%
Project 5 | Project 5 - Task 6 | Person 3 | 2025-01-15 | 10 | 25%
Project 5 | Project 5 - Task 7 | Person 4 | 2025-01-15 | 10 | 85%
Project 5 | Project 5 - Task 8 | Person 5 | 2025-01-15 | 3 | 75%
Project 6 | Project 6 - Task 1 | Person 1 | 2025-01-09 | 5 | 65%
Project 6 | Project 6 - Task 2 | Person 2 | 2025-01-10 | 6 | 20%
Project 6 | Project 6 - Task 3 | Person 3 | 2025-01-11 | 10 | 75%
Project 6 | Project 6 - Task 4 | Person 4 | 2025-01-14 | 9 | 95%
Project 6 | Project 6 - Task 5 | Person 5 | 2025-01-10 | 4 | 40%
Project 6 | Project 6 - Task 6 | Person 1 | 2025-01-13 | 6 | 0%
Project 6 | Project 6 - Task 7 | Person 2 | 2025-01-13 | 7 | 55%
Project 6 | Project 6 - Task 8 | Person 3 | 2025-01-15 | 5 | 50%
Project 7 | Project 7 - Task 1 | Person 4 | 2025-01-15 | 9 | 70%
Project 7 | Project 7 - Task 2 | Person 5 | 2025-01-16 | 6 | 55%
Project 7 | Project 7 - Task 3 | Person 1 | 2025-01-06 | 7 | 95%
Project 7 | Project 7 - Task 4 | Person 2 | 2025-01-10 | 9 | 50%
Project 7 | Project 7 - Task 5 | Person 3 | 2025-01-11 | 8 | 20%
Project 7 | Project 7 - Task 6 | Person 4 | 2025-01-13 | 7 | 55%
Project 7 | Project 7 - Task 7 | Person 5 | 2025-01-14 | 4 | 5%
Project 7 | Project 7 - Task 8 | Person 1 | 2025-01-14 | 6 | 0%
Project 7 | Project 7 - Task 9 | Person 2 | 2025-01-17 | 6 | 20%
Project 8 | Project 8 - Task 1 | Person 3 | 2025-01-18 | 4 | 15%
Project 8 | Project 8 - Task 2 | Person 4 | 2025-01-20 | 7 | 20%
Project 8 | Project 8 - Task 3 | Person 5 | 2025-01-09 | 3 | 25%
Project 8 | Project 8 - Task 4 | Person 1 | 2025-01-05 | 10 | 55%
Project 8 | Project 8 - Task 5 | Person 2 | 2025-01-14 | 5 | 45%
Project 8 | Project 8 - Task 6 | Person 3 | 2025-01-16 | 7 | 90%
Project 8 | Project 8 - Task 7 | Person 4 | 2025-01-19 | 7 | 40%
Project 8 | Project 8 - Task 8 | Person 5 | 2025-01-21 | 3 | 55%
Project 8 | Project 8 - Task 9 | Person 1 | 2025-01-23 | 9 | 95%
Project 8 | Project 8 - Task 10 | Person 2 | 2025-01-24 | 10 | 15%
Project 8 | Project 8 - Task 11 | Person 3 | 2025-01-09 | 4 | 5%
Project 9 | Project 9 - Task 1 | Person 4 | 2025-01-12 | 8 | 95%
Project 9 | Project 9 - Task 2 | Person 5 | 2025-01-15 | 10 | 20%
Project 9 | Project 9 - Task 3 | Person 1 | 2025-01-18 | 6 | 30%
Project 9 | Project 9 - Task 4 | Person 2 | 2025-01-18 | 4 | 85%
Project 10 | Project 10 - Task 1 | Person 3 | 2025-01-21 | 8 | 70%
Project 10 | Project 10 - Task 2 | Person 4 | 2025-01-23 | 9 | 10%
Project 10 | Project 10 - Task 3 | Person 5 | 2025-01-13 | 5 | 30%
Project 10 | Project 10 - Task 4 | Person 1 | 2025-01-12 | 3 | 25%
Project 10 | Project 10 - Task 5 | Person 2 | 2025-01-14 | 7 | 30%
Project 10 | Project 10 - Task 6 | Person 3 | 2025-01-15 | 10 | 5%
Project 10 | Project 10 - Task 7 | Person 4 | 2025-01-15 | 10 | 70%
Project 10 | Project 10 - Task 8 | Person 5 | 2025-01-15 | 3 | 85%
2.
Input Your Tasks of Your Project and Respective Timelines

## Advanced Project Plan Template
Ultimate Project Plan Advanced Excel Template
The Most Powerful Project Planning Template on the Market
View Details 4
Our Most Popular Project Management Templates
Excel Templates | PowerPoint Templates | MS Word Templates
Browse All Templates4