## Slide 1
STRATEGIC WINDOW: 07 APR — 07 JUN 2024 STATUS: ON TRACK / AHEAD
Executive Status: Priority Items Update
SIT & Bank Certification Portfolio Readiness
PORTFOLIO PERFORMANCE MATRIX
Stream / Initiative | Current Status | Pass Rate | Target Date
BDM Stream (21 Apps) | Lot 4-12 Execution Complete | 88% | 31 May 2024
PAY Stream (10 Apps) | Certification Ready | 100% | 13 May 2024
IRIS Priority | Validation Finalized | 100% | 01 May 2024
CBPR / SYB / MYA | Ongoing Validation | 66% (Avg) | Week 2 May
MPR Ancillary | Initial Verification Phase | 44% | 13 May 2024
RISKS & EXCEPTIONS
Critical Path & Dependencies
BDRD Migration: Sequential data load verified for KMKL environment, followed by promotion to UATBDM. Execution Strategy: Final SIT runs for UOC (User Observation Comments) prioritized to prevent certification spillover.
MILESTONE TRACKING
Resource Constraint: CBPR (74%) progress impacted by App Team bandwidth. Technical triage initiated to clear week 2 May target. Data Dependency: Snowflake delivery remains the critical path for App 65-66 (PAY Stream) to maintain 100% status for certification.
Execution Commencement 27 April
Bank Certification Start 13 May
SIT / CB Final Closure 31 May
Project Handover 07 June

## Slide 2
https://interiordesign.net/wp-content/uploads/2024/05/schiller_projects-three_cairns_group.jpg
Source: interiordesign.net
Image Sources